## Data
Sprint | Current Sprint |  | Velocity - Planned | Plan Burndown | Plan Value (points) | Plan Value (%) | Velocity - Actual | Velocity - Actual Completed (AC) | Velocity - Avg | Velocity - Rolling 3 Avg | Points Added / (Removed) | Total Points Projected (EAC) | Points Remaining | Velocity - Projected | Points Projected (ETC) | Earned Value Percent (EV%) | Earned Value (EV) (points) | SPI
0 | -1 |  | 0 | 1000 | 0 | 0% | 0 | 0 |  |  | 1000 | 1000 | 1000 | #N/A | #N/A | 0% | 0 | #N/A
1 | -1 |  | 50 | 950 | 50 | 5% | 50 | 50 | 83.3333 |  | 0 | 1000 | 950 | #N/A | #N/A | 5% | 50 | 100%
2 | -1 |  | 100 | 850 | 150 | 15% | 100 | 150 | 83.3333 |  | 25 | 1025 | 875 | #N/A | #N/A | 14.63% | 146.3415 | 97.56%
3 | -1 |  | 150 | 700 | 300 | 30% | 100 | 250 | 83.3333 | 83.3333 | 25 | 1050 | 800 | #N/A | #N/A | 23.81% | 238.0952 | 79.37%
4 | -1 |  | 100 | 600 | 400 | 40% | 100 | 350 | 83.3333 | 87.5 | -30 | 1020 | 670 | #N/A | #N/A | 34.31% | 343.1373 | 85.78%
5 | -1 |  | 100 | 500 | 500 | 50% | 75 | 425 | 83.3333 | 93.75 | 10 | 1030 | 605 | #N/A | #N/A | 41.26% | 412.6214 | 82.52%
6 | 1 |  | 150 | 350 | 650 | 65% | 75 | 500 | 83.3333 | 87.5 | 0 | 1030 | 530 | #N/A | 530 | 48.54% | 485.4369 | 74.68%
7 | 0 |  | 150 | 200 | 800 | 80% | 0 | #N/A | 83.3333 | 87.5 | 0 | #N/A | #N/A | 135 | 395 | #N/A | #N/A | #N/A
8 | 0 |  | 50 | 150 | 850 | 85% | 0 | #N/A | 83.3333 | 87.5 | 0 | #N/A | #N/A | 135 | 260 | #N/A | #N/A | #N/A
9 | 0 |  | 50 | 100 | 900 | 90% | 0 | #N/A | 83.3333 | 87.5 | 0 | #N/A | #N/A | 135 | 125 | #N/A | #N/A | #N/A
10 | 0 |  | 100 | 0 | 1000 | 100% | 0 | #N/A | 83.3333 | 87.5 | 0 | #N/A | #N/A | 125 | 0 | #N/A | #N/A | #N/A
6
The Current Sprint column is used to indicate which is the current sprint that we have completed.
-1: This sprint is before the current one done
1: This is the most recent sprint completed.
0: This sprint is not as yet completed.
AC: | (Actual Completed) How many points have actually been completed.
EAC: | (Estimate At Completion) How many points will be done by the time that the project will be completed.
ETC: | (Estimate To Complete) How many points are needed to complete the project.
SPI: | (Schedule Performance Index) Are we on track or not? 100%: we are on schedule; greater than that we are ahead of schedule; less than that we are behind schedule.